## Sheet1
Recreation & Leisure Action Plan
Date raised | Action | Details | Update | Target date | Responsible | Progress | Notes
2023-02-01 | Pavilion snagging issues | Works following the water leak were not done to the standard expected | Completion date 24 Mar-23 | 2023-03-01 | LB | 2023-03-27
2023-02-01 | Replacement kissing gate at Westend. | Invoice pending and delivery/ installation will be after April. | Confirmation of start date from Cotswold Warden to be received | 2023-04-01 | JE
2024-02-01 | Medium- long term play area reports | Currently being drafted by the Projects Officer. |  | Summer 2023 | LB / JE
2023-02-01 | Handyperson and grounds maintenance contracts | Currently advertised on the portal with a deadline date of 20th March. A meeting will be held on Wednesday 22nd March to award the contracts. | Contracts awarded at FC 22 March-23. Handyperson - DR Howse. Grounds Maintenance - CPS | 2023-04-01 | JW/ LB |  | Contracts awarded but not signed
2023-02-01 | Westend boundary footpath | Address drop at end of footpath | Developer has now changed the boundary wall by adding a fence. Still undecided if the fence will continue further along boundary. Wait for developer to finish before deciding what we need to do. | 2023-04-19 | LB
2023-03-01 | Westend footpath width | Width of public footpath has narrowed in places due to allotments spreading over the years | Deputy to contact the first 5 plots and ask them to reduce the boundary of their plot to allow for 1.2m width. If they have not done this within a few months, Deputy and Cllr Gough will mark out the boundary line | Letter to be sent by 21/04/2023 - with work to be completed by 31/06/2023 | Cllr GG/ LB
2023-02-01 | Jubilee entrance sign | New welcome sign for Jubilee | Company awarded contract. Installation due 23/24 March-23 | 2023-03-28 | JE | 2023-03-28
2023-03-01 | Flowerbed at Cam Pitch war memorial | committee agreed 3 quotes to complete the works | Contract awarded to DR Howse | 2023-03-01 |  | 2023-03-23
2023-03-01 | Jubilee car park improvements | Recommendation made to FC to award contract to company B | Agreed at FC in March. Site meeting on 18/04/2023 to agree start date | 2023-05-01 | JE
2023-03-01 | Playground inspections | Issues raised concerning the accuracy of reporting the monthly inspections | Deputy has requested more information and new photos for the April report. Cllr Gough to attend the next inspection on 6th April, 9am | on going | R&L Cllr GG
2023-03-01 | Contact Proludic regards gravel footpath at Jubilee | Gravel has not embedded as hoped | Deputy contact Proludic | 2023-05-01 | LB | 2023-04-04
2023-03-01 | Allotment competition | Judging to be carried out during regular inspections | Photos of each site taken Feb-23 | 2023-10-01 | LB/ Cllr MC | ongoing
2023-03-01 | GDPR issues relating to allotment competition blanket entry | Cllr Bishop expressed concern that blanket entry into the allotment competition contradicted our Data Protection Policy | Cllr Bishop to review policy and report back | 2023-05-01 | Cllr JB | Completed 07/06/2023
2023-03-01 | Working party for Community Events | Projects Officer to set up a working party to explore community events following the success of the bird box making session |  | 2023-11-30 | JE/ Cllr DA
2023-06-01 | Report of ASB in car park | Deputy will liaise with PCSO | 2 incidents. One received a letter, the other received a house visit. | 2023-06-30 | LB | Completed 11/07/2023
2023-07-01 | Teen Shelter/ Zone | Projects Officer to draw up a 'call out' for professional services to engage in a consultantion with young people |  | 2023-09-01 | JE | Call out advertised
2023-06-01 | Investigate solutions to problem birds at Jubilee | Bird droppings on equipment is excessive and prevents some pieces being used. | Handyman paid extra to clean twice a week over 1 month to see how bad it is. Light-hearted poster to go up. Alternative solutions investigated. | 2023-09-01 | LB | Regular cleaning is satisfactory
2023-06-01 | Create new accessible route from Westend | £1,500 allocated to purchase 5 new kissing gates | Dependent on Cotswold Warden timescales | Spring 2024 | JE/ Cotswold Wardens
2023-03-01 | Wheelchair carousel surface at Jubilee | Ground surrounding the assessible carousel has dipped again | Still under warentee, Installer to address | Priority | Sutcliffe | Complated 13/07/2023
2023-06-01 | Loose bolts on climbing frame at Cam Green | Highlighted on inspection |  | Priority | Handyperson | completed 21/07/2023
2023-06-01 | Skate park bolt missing | Highlighted on inspection | On hole in concrete so cannot replace | N/A | Handyperson | No action required
| seeding of area around car park | Recommended to Full Council in July | Council RESOLVED to plant wildflower & grass seed as approved by Working Party and R&L Committee and agreed to a maximum budget of £1,700.00 plus VAT delegated to the Clerk and Cllr Gough for the ground prep, seed sowing and watering | 2024-04-01 | JW/ Cllr GG
2023-07-01 | Review Jubilee Playing Fields 5-year action plan | Projects Officer to set up a working party to review the 5 year plan |  | 2023-12-01 | JE/ Working party
2023-10-01 | boardwalk slip surface | Surface of the boardwalk is slippery when wet | Cllr Fulchur in the process of gathering 3 quotes |  | Cllr Fulcher
2023-10-01 | Pavilion water system drained for winter | Water in the Pavilion must be drained to prevent burst pipes when it freezes | Cllr Gough to meet with Chair of Everside FC |  | Cllr Gough | 2023-11-11
Upcoming | Teen Shelter / zone review of submissions